## Read me
Corporate Business Alliance
Month-end close calendar
A close calendar and task tracker: every task with its owner, reviewer, dependency and working day, a status for each, and a sheet for the measures that show whether the close is improving.
How to use it
1. | Replace the example tasks with your own close tasks. Working days are relative to period-end: day 1 is the first working day after it, negative days are before it.
2. | For each task record the owner, the reviewer and the task it depends on, then mark whether it sits on the critical path.
3. | Update the status during the close. Blocked tasks are shaded.
4. | After each close, record the measures on Close measures and review what ran late.
Sheets
Close tasks | Every task, by working day, with owner, reviewer, dependency and status.
Close measures | Days to issue, post-close adjustments, reconciliations on time and journal rejections, month by month.
Conventions
Blue text | An input. Replace it with your own figures.
Black text | A formula. Do not overwrite it.
Grey italic | Example data, included to show how the template works. Delete or replace it.
Published by the Corporate Business Alliance, September 2026. Free to use and adapt within your organisation. The template supports good practice; it is not advice on the circumstances of any particular organisation.

## Close tasks
Close calendar
Working day 0 is period-end. Grey italic = example tasks.
ID | Task | Area | Owner | Reviewer | Depends on | Start day | Due day | Duration (days) | Status | Critical path | Notes | Summary
P1 | Bank accounts reconciled to the latest statement | Cash |  |  |  | -3 | -1 |  | Not started | No |  | Last due day
P2 | Intercompany charges cut off and raised | Intercompany |  |  |  | -3 | -3 |  | Not started | Yes |  | Tasks complete
P3 | Recurring journals prepared from schedules | Ledger |  |  |  | -2 | -1 |  | Not started | No |  | Tasks blocked
P4 | Pre-close review of the ledger for unusual entries | Ledger |  |  |  | -1 | -1 |  | Not started | No
C1 | Sales cut-off confirmed | Revenue |  |  |  | 1 | 1 |  | Not started | Yes
C2 | Purchase cut-off confirmed and accruals posted | Payables |  |  | C1 | 1 | 2 |  | Not started | Yes
C3 | Payroll journal posted | Payroll |  |  |  | 1 | 1 |  | Not started | No
C4 | Intercompany balances agreed with counterparties | Intercompany |  |  | P2 | 1 | 2 |  | Not started | Yes
C5 | Depreciation posted from the fixed asset register | Fixed assets |  |  | P3 | 1 | 1 |  | Not started | No
C6 | Manual journals approved | Ledger |  |  | C2 | 1 | 3 |  | Not started | No
C7 | Balance sheet reconciliations prepared | Balance sheet |  |  | C2 | 2 | 3 |  | Not started | Yes
C8 | Balance sheet reconciliations reviewed | Balance sheet |  |  | C7 | 3 | 4 |  | Not started | Yes
C9 | Trial balance review | Reporting |  |  | C8 | 3 | 4 |  | Not started | Yes
C10 | Consolidation and eliminations | Reporting |  |  | C4 | 4 | 4 |  | Not started | Yes
C11 | Management accounts pack produced | Reporting |  |  | C10 | 4 | 5 |  | Not started | Yes
C12 | Commentary drafted and reviewed | Reporting |  |  | C11 | 5 | 5 |  | Not started | Yes
C13 | Management accounts issued | Reporting |  |  | C12 | 5 | 5 |  | Not started | Yes

## Close measures
Close measures
One row per month. Record them after every close.
Month | Working days to issue | Post-close adjustments (number) | Post-close adjustments (value) | Reconciliations reviewed on time | Manual journals posted | Manual journals rejected at review | What ran late, and why
Average